## Sheet1
Thesis Schedule |  | 2020 |  |  |  |  | 2021 | [11 empty] | 2022
|  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Horsenettle Regional Comparison | Project design | bar: 2020 Aug to 2020 Dec
Proposal writing | bar: 2020 Aug to 2020 Dec
Grow plants from rhizomes | bar: 2020 Dec to 2021 Sep; 2021 Dec to 2022 Sep
Collect sporophytic tolerance data | bar: 2021 Mar to 2021 Jul
Pollen viability and tube growth rate | bar: 2021 Apr to 2021 Aug
Data analysis | bar: 2021 Sep to 2021 Oct
Pollen Competition | Genotyping all plants | bar: 2021 Jan to 2021 Sep
Pollen chase experiments | bar: 2022 Feb to 2022 Aug
Data analysis | bar: 2022 Jul to 2022 Sep
Phenology Project | Path analysis modeling | bar: 2020 Aug to 2020 Oct
Data analysis | bar: 2020 Oct to 2020 Nov
Write manuscript | bar: 2020 Nov to 2021 Jan
Revisions | bar: 2021 Jan to 2021 Mar
Thesis Writing | Chapter 1: Tolerance | bar: 2021 Nov to 2021 Dec
Chapter 2: Chase Experiment | bar: 2022 Sep to 2022 Oct
Chapter 3: Phenology Project | bar: 2021 Apr to 2021 May
Revisions | bar: 2022 Nov
Advisory Committee Meetings | bar: 2021 Mar; 2022 Mar
Defense | bar: 2022 Dec
Courses | Scientific Integrity | 2020 Aug: 1cr
| Track Course: BIOL 884 | 2020 Aug: 3cr
| Track Course: RNG 717 | 2020 Aug: 3cr
| Interdisciplinary Course: GEOL 613 | 2021 Jan: 3cr
| Track Course: STAT 669 | 2021 Jan: 3cr
| Track Course: BIOL 661 | 2021 Aug: 3cr
| Track Course: PLSC 611 | 2021 Aug: 3cr
| ECS Seminar | 2022 Sep: 1cr
| Thesis | 2020 Aug: 1 cr; 2021 Jan: 1cr; 2021 Jun: 1cr; 2021 Aug: 1cr; 2022 Jan: 3cr; 2022 Jun: 1cr; 2022 Sep: 2cr

## Sheet2
Data Collection Timeline | 2 months | Days
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Growth from Rhizome
CMS - heat | bar: Days 1
Photosynthesis - heat |  | Days 7: Waiting
CMS - cold |  | Days 19: Waiting; Days 32: Waiting
Photosynthesis- cold |  | Days 19: Waiting; Days 32: Waiting
Pollen tube growth rate | bar: Days 45 to Days 50
Pollen grain viability | bar: Days 45 to Days 50